## Test Plan
Please Click Here to show my testplan for TECHLAND BD

## TestScenarios
Project Name | TECHLAND BD
Reference Document | FRS
Created By | MD Shahriar Khan Shuvo
Creation Date | 2026-03-14
Approval Date | 2026-03-14
Test Scenario ID | Reference | Test Scenario Description | Priority | Number of Test Cases
TS_001 |  | Validate the URL in different browsers. | P0 | 1
TS_002 |  | Validate the "Register Account" functionality | P1 | 72
TS_003 |  | Validate the working of the "Login" functionality. | P0 | 0

## TestCase
Product Name |  | Techland | TC Start Date | 2026-03-10 | TC Execution Start Date | - - |  |  |  |  | TEST CASE
Module Name |  | Account | TC End Date | 2026-08-14 | TC Execution End Date | - - |  |  |  |  | PASS | 72
Epic |  |  | Test Case Developed By | MD Shahriar Khan Shuvo | Browser (tested) | Yes |  |  |  |  | FAIL | 13
Developer Name (TL) |  |  | Test Case Reviewed By | Rubel Hosain | Performance (tested) | Yes |  |  |  |  | NO RUN | 0
Test Executed by | [10 empty] | BLOCKED | 0
[11 empty] | TOTAL | 85
#SL | Module | Type of Testing | Features | Test Cases | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bugs Screen Shot | Dev Comments | Final Status | Remarks
1 | Account | Browser Compatibility Testing | Browser | Verify that the URL site in different browsers. | Should be run in different Browsers | Successfully run in different browaer. | Md Shahriar Khan Shuvo 01621957382 shuvo200144@gmail.com 12345676 | 1. Goto different browsers 2. Search 'Techland' 3. Goto the website |  |  | Passed
Test cases for registration (name ) module
2 | Account | Functional | Name | Verify full name field with valid full name | Should be accepted | Accepted | Md Shahriar Khan Shuvo 01621957382 shuvo200144@gmail.com 12345678 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data |  |  | Passed
3 | Account | Functional | Name | Verify full name field with one alphabet only | Should be accepted | Accepted | Md' Shahriar Khan Shuvo 01621957382 shuvo200144@gmail.com 12345679 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fill Full name field with only one alphabet |  |  | Passed
4 | Account | Functional | Name | Verify full name field with apostrophe in name | Should be accepted | Accepted | M 01621957382 shuvo200144@gmail.com 12345680 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fill Full name field with apostrophe in name |  |  | Passed
5 | Account | Functional | Name | Verify full name field with long valid name | Should be accepted | Accepted | Ikhtiar Uddin Mohammad Bin Bokhtiar Khilji 01621957382 shuvo200144@gmail.com 12345681 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fill Full name field with long valid name |  |  | Passed
6 | Account | Functional | Name | Verify full name field with empty field | Regirstration Failed | Rgistration Failed | empty name field 01621957382 shuvo200144@gmail.com 12345682 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Don't write anything on the name field |  |  | Passed
7 | Account | Functional | Name | Verify full name field pop-up message with empty field | A pop-up message should be shown | A pop-up message has been shown | empty name field 01621957382 shuvo200144@gmail.com 12345683 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Don't write anything on the name field |  |  | Passed
8 | Account | Functional | Name | Verify full name field by giving spaces in between every letter of a name | Should be accepted | Accepted | M d S h a h r I a r K h a n S h u v o 01621957382 shuvo200144@gmail.com 12345684 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6Full fill the name field by giving spaces after every letter of a name |  |  | Passed
9 | Account | Functional | Name | Verify full name field with only spaces in the field | Should not be accepted | Registration Failed | " " 01621957382 shuvo200144@gmail.com 12345685 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Full fill the name field with only spaces |  |  | Passed
10 | Account | Functional | Name | Verify full name field with special characters in the name | Should not be accepted | Registration Failed | # Md Shahrir Khan Shuvo 01621957382 shuvo200144@gmail.com 12345686 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Full fill the name field with special character in the name |  |  | Passed
11 | Account | Functional | Name | Verify full name field with only special character | Should not be accepted | Registration Failed | # $%^&* 01621957382 shuvo200144@gmail.com 12345687 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Full fill the name field with only special character |  |  | Passed
12 | Account | Functional | Name | Verify full name field with very very long name | Should not be accepted | Accepted | kjsdjasjghdgasfgdjsafjhdhasdgksjagdjkagkjdgjkasgjdkgasjkdgjkasgjdkgasjkdgjkagdkjagsjkdgkjasgjkdg 01621957382 shuvo200144@gmail.com 12345688 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Full fill the name field with very long name | bug screenshot |  | Failed
13 | Account | Functional | Name | Verify full name field with hyphen in the name | Should be accepted | Accepted | Md Shahriar-Khan Shuvo 01621957382 shuvo200144@gmail.com 12345689 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Full fill the name field with hyphen in the name |  |  | Passed
14 | Account | Functional | Name | Verify full name field with hyphen after every letter of the name | Should be accepted | Accepted | M-d-S-h-a-h-r-i-a-r 01621957382 shuvo200144@gmail.com 12345690 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Full fill the name field with hyphen after every letter |  |  | Passed
15 | Account | Functional | Name | Verify full name field with only numbers | Should not be accepted | Accepted | 12345678910 01621957382 shuvo200144@gmail.com 12345691 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Full fill the name field with only numbers | number only bug |  | Failed
16 | Account | Functional | Name | Verify full name field with dot in the name | Should be accepted | Accepted | Md.Shahriar Khan Shuvo 01621957382 shuvo200144@gmail.com 12345691 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Full fill the name field with dot in the name |  |  | Passed
Test cases for registration (Phone Number) module
17 | Account | Functional | Phone Number | Verify phone number field with empty | should be a pop-up message | A pop-up message has been shown | Md.Shahriar Khan Shuvo empth field shuvo200144@gmail.com 12345693 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Don't write anything on the the number field |  |  | Passed
18 | Account | Functional | Phone Number | Verify phone number field valid mobile number | Should be accepted | Accepted | Md.Shahriar Khan Shuvo 01754115482 shuvo200144@gmail.com 12345694 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Full fill the number field with valid number |  |  | Passed
19 | Account | Functional | Phone Number | Verify phone number field with country code valid number | Should be accepted | Accepted | Md.Shahriar Khan Shuvo + 8801754115482 shuvo200144@gmail.com 12345695 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Full fill the number field with cpuntry code and valid number |  |  | Passed
20 | Account | Functional | Phone Number | Verify phone number field with spaces between numbers | Should not be accepted | Registration Failed | Md.Shahriar Khan Shuvo + 8 80 17 5411 54 8 2 shuvo200144@gmail.com 12345696 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Full fill the number field giving spaces between valid numbers |  |  | Passed
21 | Account | Functional | Phone Number | Verify phone number field with only spaces | Should not be accepted | Registration Failed | Md.Shahriar Khan Shuvo " " shuvo200144@gmail.com 12345697 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Full fill the number field with only spaces |  |  | Passed
22 | Account | Functional | Phone Number | Verify phone number field with mobile number with letters | Should not be accepted | Registration Failed | Md.Shahriar Khan Shuvo 0175411sd82 shuvo200144@gmail.com 12345698 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Full fill the number field mobile number with letters |  |  | Passed
23 | Account | Functional | Phone Number | Verify phone number field with only letters | Should not be accepted | Registration Failed | Md.Shahriar Khan Shuvo sddfsfefsdfsg shuvo200144@gmail.com 12345699 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Full fill the number field with only letters |  |  | Passed
24 | Account | Functional | Phone Number | Verify phone number field with special characters in the mobile numbre | Should not be accepted | Registration Failed | Md.Shahriar Khan Shuvo 017541154@2 shuvo200144@gmail.com 12345700 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Full fill the number field with special characters in the number |  |  | Passed
25 | Account | Functional | Phone Number | Verify phone number field with only special characters in the mobile numbre | Should not be accepted | Registration Failed | Md.Shahriar Khan Shuvo @@@@@@@@@@@@ shuvo200144@gmail.com 12345701 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Full fill the number field with only special characters in the number |  |  | Passed
26 | Account | Functional | Phone Number | Verify phone number field with mobile number with symbols | Should not be accepted | Registration Failed | Md.Shahriar Khan Shuvo 01754#11548 shuvo200144@gmail.com 12345702 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Full fill the number field with mobile number with symbols |  |  | Passed
27 | Account | Functional | Phone Number | Verify phone number field with only symbols | Should not be accepted | Registration Failed | Md.Shahriar Khan Shuvo $$$$$$$$########## shuvo200144@gmail.com 12345703 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Full fill the number field with only symbols |  |  | Passed
28 | Account | Functional | Phone Number | Verify phone number field with mobile number shorter than required length | Should not be accepted | Registration Failed | Md.Shahriar Khan Shuvo 0175411548 shuvo200144@gmail.com 12345704 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Full fill the number field with mobile number shorter than required length |  |  | Passed
29 | Account | Functional | Phone Number | Verify phone number field with mobile number longer than required length | Should not be accepted | Registration Failed | Md.Shahriar Khan Shuvo 017541154823 shuvo200144@gmail.com 12345705 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Full fill the number field with mobile number longer than required length |  |  | Passed
30 | Account | Functional | Phone Number | Verify phone number field with starting with invalid prefix | Should not be accepted | Registration Failed | Md.Shahriar Khan Shuvo 01175411548 shuvo200144@gmail.com 12345706 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Full fill the number field with starting with invalid prefix |  |  | Passed
31 | Account | Functional | Phone Number | Verify phone number field with starting with decimal numbers | Should not be accepted | Registration Failed | Md.Shahriar Khan Shuvo 011754.11548 shuvo200144@gmail.com 12345707 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Full fill the number field with decimal numbers |  |  | Passed
32 | Account | Functional | Phone Number | Verify phone number field with starting with negative numbers | Should not be accepted | Registration Failed | Md.Shahriar Khan -01175411548 shuvo200144@gmail.com 12345708 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Full fill the number field with negative numbers |  |  | Passed
33 | Account | Functional | Phone Number | Verify phone number field with mobile number with spaces in between | Should not be accepted | Registration Failed | Md.Shahriar Khan 0 11754 11548 shuvo200144@gmail.com 12345709 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Full fill the number field with mobile number with spaces in between |  |  | Passed
34 | Account | Functional | Phone Number | Verify phone number field with mobile number with only spaces | Should not be accepted | Registration Failed | Md.Shahriar Khan " " shuvo200144@gmail.com 12345710 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Full fill the number field with mobile number with only spaces |  |  | Passed
35 | Account | Functional | Phone Number | Verify phone number field with mobile number with hyphen | Should not be accepted | Registration Failed | Md.Shahriar Khan 01754-115482 shuvo200144@gmail.com 12345711 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Full fill the number field with mobile number with hyphen |  |  | Passed
36 | Account | Functional | Phone Number | Verify phone number field with mobile number Unicode characters | Should not be accepted | Registration Failed | Md.Shahriar Khan 01754-115482 shuvo200144@gmail.com 12345712 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Full fill the number field with mobile number unicode characters |  |  | Passed
Test cases for Registration(Email Address) Module
37 | Account | Functional | Email Address | Verify Email Address field with empty field | should not be accepted | Rejected | Md.Shahriar Khan 01754-115482 " " 12345712 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Don't write anything on the email address field |  |  | Passed
38 | Account | Functional | Email Address | Verify Email Address field pop-up messahe with empty email address | Input valid email address | Please fill out this field | Md.Shahriar Khan 01754-115482 " " 12345713 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Don't write anything on the email address field |  |  | Failed
39 | Account | Functional | Email Address | Verify Email Address field with email with numbers | Should be Accepted | Accepted | Md.Shahriar Khan 01754-115482 shuvo200144@gmail.com 12345714 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the email address field with email with numbers |  |  | Passed
40 | Account | Functional | Email Address | Verify Email Address field with email with underscore | Should be Accepted | Accepted | Md.Shahriar Khan 01754-115482 shuvo_200144@gmail.com 12345715 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the email address field with email with underscore |  |  | Passed
41 | Account | Functional | Email Address | Verify Email Address field with email with hyphen | Should be Accepted | Accepted | Md.Shahriar Khan 01754-115482 shuvo-200144@gmail.com 12345716 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the email address field with email with hyphen |  |  | Passed
42 | Account | Functional | Email Address | Verify Email Address field with email with only spaces | Should not be Accepted | Rejected | Md.Shahriar Khan 01754-115482 " " 12345717 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the email address field with email with only spaces |  |  | Passed
43 | Account | Functional | Email Address | Verify Email Address field with email without '@' symbol | Should not be Accepted | Rejected | Md.Shahriar Khan 01754-115482 shuvo200144 gmail.com 12345718 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the email address field with email without '@' symbol |  |  | Passed
44 | Account | Functional | Email Address | Verify Email Address field with email without domain name | Should not be Accepted | Rejected | Md.Shahriar Khan 01754-115482 shuvo200144 12345719 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the email address field with email without domain name |  |  | Passed
45 | Account | Functional | Email Address | Verify Email Address field with email without username | Should not be Accepted | Rejected | Md.Shahriar Khan 01754-115482 @gmail.com 12345720 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the email address field with email without username |  |  | Passed
46 | Account | Functional | Email Address | Verify Email Address field with email without top-level domain | Should not be Accepted | Rejected | Md.Shahriar Khan 01754-115482 shuvo200144@gmail 12345721 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the email address field with email without top-level domain |  |  | Passed
47 | Account | Functional | Email Address | Verify Email Address field with multiple '@' symbols | Should not be Accepted | Rejected | Md.Shahriar Khan 01754-115482 shuvo200144@@@gmail.com 12345722 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the email address field with multiple '@' symbols |  |  | Passed
48 | Account | Functional | Email Address | Verify Email Address field with spaces inside email | Should not be Accepted | Rejected | Md.Shahriar Khan 01754-115482 shuvo200144@gmail.com 12345723 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the email address field with spaces inside email |  |  | Passed
49 | Account | Functional | Email Address | Verify Email Address field with special characters | Should not be Accepted | Rejected | Md.Shahriar Khan 01754-115482 shuvo200144#gmail.com 12345724 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the email address field with spaces inside email |  |  | Passed
50 | Account | Functional | Email Address | Verify Email Address field with email starting with dot | Should not be Accepted | Rejected | Md.Shahriar Khan 01754-115482 .shuvo200144#gmail.com 12345725 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the email address field with email starting with dot |  |  | Passed
51 | Account | Functional | Email Address | Verify Email Address field with email ending with dot | Should not be Accepted | Rejected | Md.Shahriar Khan 01754-115482 shuvo200144.@gmail.com 12345726 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the email address field with email starting with dot |  |  | Passed
52 | Account | Functional | Email Address | Verify Email Address field with email with consecutive dots | Should not be Accepted | Rejected | Md.Shahriar Khan 01754-115482 shuvo200144...@gmail.com 12345727 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the email address field with email with consecutive dots |  |  | Passed
53 | Account | Functional | Email Address | Verify Email Address field with email uppercase letters | Should be Accepted | Accepted | Md.Shahriar Khan 01754-115482 ABCD@gmail.com 12345728 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the email address field with uppercase letters |  |  | Passed
54 | Account | Functional | Email Address | Verify Email Address field with long valid email | Should be Accepted | Accepted | Md.Shahriar Khan 01754-115482 kjskdagskjdkjasjksjdksagkd@gmail.com 12345729 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the email address field with long valid email |  |  | Passed
55 | Account | Functional | Email Address | Verify Email Address field with domain starting with hyphen | Should not be Accepted | Rejected | Md.Shahriar Khan 01754-115482 shuvo200144@-gmail.com 12345730 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the email address field with domain starting with hyphen |  |  | Passed
56 | Account | Functional | Email Address | Verify Email Address field with domain ending with hyphen | Should not be Accepted | Rejected | Md.Shahriar Khan 01754-115482 shuvo200144@gmail-.com 12345730 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the email address field with domain ending with hyphen |  |  | Passed
57 | Account | Functional | Email Address | Verify Email Address field with email without dot in domain | Should not be Accepted | Rejected | Md.Shahriar Khan 01754-115482 shuvo200144@gmailcom 12345731 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the email address field with email without dot in domain |  |  | Passed
58 | Account | Functional | Email Address | Verify Email Address field with valid organizational email | Should be Accepted | Accepted | Md.Shahriar Khan 01754-115482 shuvo15-5275@diu.edu.bd 12345732 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the email address field with valid organizational email |  |  | Passed
59 | Account | Functional | Email Address | Verify Email Address field with country domain email | Should be Accepted | Accepted | Md.Shahriar Khan 01754-115482 shuvo@gmail.co.uk 12345733 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the email address field with country domain email |  |  | Passed
60 | Account | Functional | Email Address | Verify Email Address field with numeric-only email | Should not be Accepted | Rejected | Md.Shahriar Khan 01754-115482 1234567 12345734 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the email address field with numeric-only email |  |  | Passed
Test Cases for Registration(Password) Module
61 | Account | Functional | Password | Verify password field with valid password | Shpuld be accepted | Accepted | Md.Shahriar Khan 01754115482 12345678 12345678 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the password field with valid password |  |  | Passed
62 | Account | Functional | Password | Verify password field with minimum length password | Shpuld be accepted | Accepted | Md.Shahriar Khan 01754115482 12345678 12345679 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the password field with minimum length password |  |  | Passed
63 | Account | Functional | Password | Verify password field with less than minimum characters | Shpuld not be accepted | Rejected | Md.Shahriar Khan 01754115482 1234567 1234567 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the password field with less than minimum characters |  |  | Passed
64 | Account | Functional | Password | Verify password field with very long password | Shpuld be accepted | Accepted | Md.Shahriar Khan 01754115482 123456716336118761876813 123456716336118761876813 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the password field with very long password |  |  | Passed
65 | Account | Functional | Password | Verify password field with only numbers | Shpuld be accepted | Accepted | Md.Shahriar Khan 01754115482 123456716336118761876813 123456716336118761876813 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the password field with only numbers |  |  | Passed
66 | Account | Functional | Password | Verify password field with number and letter mixed | Shpuld be accepted | Accepted | Md.Shahriar Khan 01754115482 1234asdasd 1234asdasd | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the password field with number and letter mixed |  |  | Passed
67 | Account | Functional | Password | Verify password field with only alphabets | Shpuld be accepted | Accepted | Md.Shahriar Khan 01754115482 asasdasd asasdasd | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the password field with only alphabets |  |  | Passed
67 | Account | Functional | Password | Verify password field with only special characters | Shpuld be accepted | Rejected | Md.Shahriar Khan 01754115482 @@#$%^&* @@#$%^&* | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the password field with only special characters | wrong password message |  | Failed
68 | Account | Functional | Password | Verify password field with letters, numbers, and special characters | Shpuld be accepted | Accepted | Md.Shahriar Khan 01754115482 1234568sad@# 1234568sad@# | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the password field with letters, numbers, and special characters |  |  | Passed
69 | Account | Functional | Password | Verify password field with Leave password field empty | Shpuld not be accepted | Rejected | Md.Shahriar Khan 01754115482 " " " " | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6. Leave password field empty |  |  | Passed
70 | Account | Functional | Password | Verify password field with spaces between password | Shpuld not be accepted | Accepted | Md.Shahriar Khan 01754115482 abcd efgh abcd efgh | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the password field with spaces between passwords |  |  | Failed
71 | Account | Functional | Password | Verify password field with only spaces | Shpuld be displayed a error message | Reload the page | Md.Shahriar Khan 01754115482 only spaces only spaces | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the password field with only spaces |  |  | Failed
72 | Account | Functional | Password | Verify password field with uppercase letters | Shpuld be displayed strong password required | Accepted | Md.Shahriar Khan 01754115482 ABCDEFGH ABCDEFGH | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the password field with only uppercase letters |  |  | Failed
73 | Account | Functional | Password | Verify password field with lowercase letters | Shpuld be displayed strong password required | Accepted | Md.Shahriar Khan 01754115482 abcdefgh abcdefgh | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the password field with lowercase letters |  |  | Failed
Test Cases for Account login(Phone Number) Module
74 | Account | Functional | Phone Number | Verify phone number field with empty | should be a pop-up message | A pop-up message has been shown | Md.Shahriar Khan Shuvo empth field shuvo200144@gmail.com 12345693 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Don't write anything on the the number field |  |  | Passed
75 | Account | Functional | Phone Number | Verify phone number field valid mobile number | Should be accepted | Accepted | Md.Shahriar Khan Shuvo 01754115482 shuvo200144@gmail.com 12345694 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Full fill the number field with valid number |  |  | Passed
76 | Account | Functional | Phone Number | Verify phone number field with country code valid number | Should be accepted | Accepted | Md.Shahriar Khan Shuvo + 8801754115482 shuvo200144@gmail.com 12345695 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Full fill the number field with cpuntry code and valid number |  |  | Passed
77 | Account | Functional | Phone Number | Verify phone number field with spaces between numbers | Should not be accepted | Registration Failed | Md.Shahriar Khan Shuvo + 8 80 17 5411 54 8 2 shuvo200144@gmail.com 12345696 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Full fill the number field giving spaces between valid numbers |  |  | Passed
78 | Account | Functional | Phone Number | Verify phone number field with only spaces | Should not be accepted | Registration Failed | Md.Shahriar Khan Shuvo " " shuvo200144@gmail.com 12345697 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Full fill the number field with only spaces |  |  | Passed
79 | Account | Functional | Phone Number | Verify phone number field with mobile number with letters | Should not be accepted | Registration Failed | Md.Shahriar Khan Shuvo 0175411sd82 shuvo200144@gmail.com 12345698 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Full fill the number field mobile number with letters |  |  | Passed
80 | Account | Functional | Phone Number | Verify phone number field with only letters | Should not be accepted | Registration Failed | Md.Shahriar Khan Shuvo sddfsfefsdfsg shuvo200144@gmail.com 12345699 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Full fill the number field with only letters |  |  | Passed
81 | Account | Functional | Phone Number | Verify phone number field with special characters in the mobile numbre | Should not be accepted | Registration Failed | Md.Shahriar Khan Shuvo 017541154@2 shuvo200144@gmail.com 12345700 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Full fill the number field with special characters in the number |  |  | Passed
82 | Account | Functional | Phone Number | Verify phone number field with only special characters in the mobile numbre | Should not be accepted | Registration Failed | Md.Shahriar Khan Shuvo @@@@@@@@@@@@ shuvo200144@gmail.com 12345701 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Full fill the number field with only special characters in the number |  |  | Passed
83 | Account | Functional | Phone Number | Verify phone number field with mobile number with symbols | Should not be accepted | Registration Failed | Md.Shahriar Khan Shuvo 01754#11548 shuvo200144@gmail.com 12345702 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Full fill the number field with mobile number with symbols |  |  | Passed
84 | Account | Functional | Phone Number | Verify phone number field with only symbols | Should not be accepted | Registration Failed | Md.Shahriar Khan Shuvo $$$$$$$$########## shuvo200144@gmail.com 12345703 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Full fill the number field with only symbols |  |  | Passed
85 | Account | Functional | Phone Number | Verify phone number field with mobile number shorter than required length | Should not be accepted | Registration Failed | Md.Shahriar Khan Shuvo 0175411548 shuvo200144@gmail.com 12345704 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Full fill the number field with mobile number shorter than required length |  |  | Passed
86 | Account | Functional | Phone Number | Verify phone number field with mobile number longer than required length | Should not be accepted | Registration Failed | Md.Shahriar Khan Shuvo 017541154823 shuvo200144@gmail.com 12345705 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Full fill the number field with mobile number longer than required length |  |  | Passed
87 | Account | Functional | Phone Number | Verify phone number field with starting with invalid prefix | Should not be accepted | Registration Failed | Md.Shahriar Khan Shuvo 01175411548 shuvo200144@gmail.com 12345706 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Full fill the number field with starting with invalid prefix |  |  | Passed
88 | Account | Functional | Phone Number | Verify phone number field with starting with decimal numbers | Should not be accepted | Registration Failed | Md.Shahriar Khan Shuvo 011754.11548 shuvo200144@gmail.com 12345707 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Full fill the number field with decimal numbers |  |  | Passed
89 | Account | Functional | Phone Number | Verify phone number field with starting with negative numbers | Should not be accepted | Registration Failed | Md.Shahriar Khan -01175411548 shuvo200144@gmail.com 12345708 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Full fill the number field with negative numbers |  |  | Passed
90 | Account | Functional | Phone Number | Verify phone number field with mobile number with spaces in between | Should not be accepted | Registration Failed | Md.Shahriar Khan 0 11754 11548 shuvo200144@gmail.com 12345709 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Full fill the number field with mobile number with spaces in between |  |  | Passed
91 | Account | Functional | Phone Number | Verify phone number field with mobile number with only spaces | Should not be accepted | Registration Failed | Md.Shahriar Khan " " shuvo200144@gmail.com 12345710 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Full fill the number field with mobile number with only spaces |  |  | Passed
92 | Account | Functional | Phone Number | Verify phone number field with mobile number with hyphen | Should not be accepted | Registration Failed | Md.Shahriar Khan 01754-115482 shuvo200144@gmail.com 12345711 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Full fill the number field with mobile number with hyphen |  |  | Passed
93 | Account | Functional | Phone Number | Verify phone number field with mobile number Unicode characters | Should not be accepted | Registration Failed | Md.Shahriar Khan 01754-115482 shuvo200144@gmail.com 12345712 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Full fill the number field with mobile number unicode characters |  |  | Passed
Test cases for account login(Password) Module
94 | Account | Functional | Password | Verify password field with valid password | Shpuld be accepted | Accepted | Md.Shahriar Khan 01754115482 12345678 12345678 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the password field with valid password |  |  | Passed
95 | Account | Functional | Password | Verify password field with minimum length password | Shpuld be accepted | Accepted | Md.Shahriar Khan 01754115482 12345678 12345679 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the password field with minimum length password |  |  | Passed
96 | Account | Functional | Password | Verify password field with less than minimum characters | Shpuld not be accepted | Rejected | Md.Shahriar Khan 01754115482 1234567 1234567 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the password field with less than minimum characters |  |  | Passed
97 | Account | Functional | Password | Verify password field with very long password | Shpuld be accepted | Accepted | Md.Shahriar Khan 01754115482 123456716336118761876813 123456716336118761876813 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the password field with very long password |  |  | Passed
98 | Account | Functional | Password | Verify password field with only numbers | Shpuld be accepted | Accepted | Md.Shahriar Khan 01754115482 123456716336118761876813 123456716336118761876813 | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the password field with only numbers |  |  | Passed
99 | Account | Functional | Password | Verify password field with number and letter mixed | Shpuld be accepted | Accepted | Md.Shahriar Khan 01754115482 1234asdasd 1234asdasd | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the password field with number and letter mixed |  |  | Passed
100 | Account | Functional | Password | Verify password field with only alphabets | Shpuld be accepted | Accepted | Md.Shahriar Khan 01754115482 asasdasd asasdasd | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the password field with only alphabets |  |  | Passed
101 | Account | Functional | Password | Verify password field with only special characters | Shpuld be accepted | Rejected | Md.Shahriar Khan 01754115482 @@#$%^&* @@#$%^&* | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the password field with only special characters | wrong password message |  | Failed
102 | Account | Functional | Password | Verify password field with letters, numbers, and special characters | Shpuld be accepted | Accepted | Md.Shahriar Khan 01754115482 1234568sad@# 1234568sad@# | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the password field with letters, numbers, and special characters |  |  | Passed
103 | Account | Functional | Password | Verify password field with Leave password field empty | Shpuld not be accepted | Rejected | Md.Shahriar Khan 01754115482 " " " " | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6. Leave password field empty |  |  | Passed
104 | Account | Functional | Password | Verify password field with spaces between password | Shpuld not be accepted | Accepted | Md.Shahriar Khan 01754115482 abcd efgh abcd efgh | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the password field with spaces between passwords |  |  | Failed
105 | Account | Functional | Password | Verify password field with only spaces | Shpuld be displayed a error message | Reload the page | Md.Shahriar Khan 01754115482 only spaces only spaces | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the password field with only spaces |  |  | Failed
106 | Account | Functional | Password | Verify password field with uppercase letters | Shpuld be displayed strong password required | Accepted | Md.Shahriar Khan 01754115482 ABCDEFGH ABCDEFGH | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the password field with only uppercase letters |  |  | Failed
107 | Account | Functional | Password | Verify password field with lowercase letters | Shpuld be displayed strong password required | Accepted | Md.Shahriar Khan 01754115482 abcdefgh abcdefgh | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the password field with lowercase letters |  |  | Failed
Negative test
mmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmm

## Test Summary Report
Test Case Report | [5 empty] | Result :
Project Name | Techland BD
Module Name | Account. |  |  |  |  | Total No. | Status
Feature Name | Register Account & Account Login.
Test Case Version | 1 |  |  |  |  | 72 | PASS
Written By | MD Shahriar Khan Shuvo |  |  |  |  | 13 | FAIL
Executed By | MD Shahriar Khan Shuvo |  |  |  |  | 0 | Not Executed
Reviewed By | Rubel Hosain |  |  |  |  | 0 | Out of Scope
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 72 | 13 | 0 | 0 | 85
Grand Total | 72 | 13 | 0 | 0 | 85
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Bug Report
Bug Reporting | Bug Reporting | Bug Reporting | Bug Reporting | Bug Reporting | Bug Reporting | Bug Reporting
# SL 01 | # SL 02 | # SL 03 | # SL 04 | # SL 05 | # SL 06 | # SL 07
Issue: Registered with very very long name | Issue: Registered with only numbers in the name field | Issue:Wrong pop-up message while emptying the field | Issue: Registered with spcaes in the password | Issue: Do nothing with only spaces in the password | Issue: Registered with only uppercase letters | Issue: Registered with only lowercase letters
Reproducing Steps: | Reproducing Steps: | Reproducing Steps: | Reproducing Steps: | Reproducing Steps: | Reproducing Steps: | Reproducing Steps:
1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Full fill the name field with very long name | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Full fill the name field with only numbers | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Don't write anything on the email address field | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the password field with spaces between passwords | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the password field with only spaces | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the password field with only uppercase letters | 1. Go to the browser. 2. Search 'Techland' 3. Go to the website. 4.Click on the Create an account button 5.Fill all the field with valid data 6.Fullfill the password field with only lowercase letters
Env: Production. | Env: Production. | Env: Production. | Env: Production. | Env: Production. | Env: Production. | Env: Production.
Module: Register | Module: Register | Module: Register | Module: Register | Module: Register | Module: Register | Module: Register
Priority: Low | Priority: Low | Priority: Low | Priority: High | Priority: High | Priority: High | Priority: High
Severity: Minor | Severity: Minor | Severity: Minor | Severity: Major | Severity: Major | Severity: Major | Severity: Major
Screenshot: Invalid very very long name | Screenshot: accepted only number in the name field | Screenshot: Wrong pop-up message | Screenshot: accepted wrong password | Screenshot: do nothing with only spaces in the password | Screenshot: Registered with only uppercase letters | Screenshot: Registered with only lowercase letters
Expected: Should not allow registration with that very long name | Expected: Should not allow registration with only numbers in the name field | Expected: Should pop-up a message of enter valid email | Expected: Should not allow registration with spaces in the password | Expected: Should pop-up a message | Expected: Should not allow registration with only uppercase in the password | Expected: Should not allow registration with only lowercase
Actual: Accepted the very long name | Actual: Accepted | Actual: Please inut this field | Actual: Accepted | Actual: reloaded the page | Actual: Accepted | Actual: Accepted
Responsible QA: Md Shahriar Khan Shuvo | Responsible QA: Md Shahriar Khan Shuvo | Responsible QA: Md Shahriar Khan Shuvo | Responsible QA: Md Shahriar Khan Shuvo | Responsible QA: Md Shahriar Khan Shuvo | Responsible QA: Md Shahriar Khan Shuvo | Responsible QA: Md Shahriar Khan Shuvo

## Test Metrics
Test Metrics
#SL | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (73/73)*100 = 100
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (0/73)*100 = 0
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (65/73)*100 = 89.04%
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (7/73)*100 = 9.58%
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/73)*100 = 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A

## Recommandation
GENERAL INFORMATION
test stage | Unit performance | Functionality Regression | Integration Acceptance | System Pilot | Interface
Specify the testing stage for this test case
Date: | mm/dd/yy |  | System Date,If Applicable |  | mm/dd/yy
Tester: | Specify the name (s)of who is testing this case scenario. |  | Test Case Number |  | Specify the unique test number assigned to the test case
Test case Description: | Provide a brief description of what functionality the test case
Results: | Pass Fail |  | Incident Number,If Applicable: |  | Specify the unique identifier assingned to the incident.
INTRODUCTION
Requirement(s) to be tested: | Identify the requirments to be tested and include the requirment number and description from the Requirments Traceability Matrix
Roles and Responsibilites: | Describe each project team member and stakeholder involved in the test, and identify their associated responsibility for ensuring the test is executed appropriately
Set Up procedures: | Describe the sequence of actions necessary to prepare for execution of the test
Stop Procedures: | Describe the sequence of actions necessary to terminate the test
ENVIRONMENTAL NEEDS
Hardware: | Identify the qualities and configurations of the hardware required to execute the test case
Software: | Identify system and application software required to execute the test case.Specify any software that the test case will interact with.
Procedural Requirments: | Describe any constraints on the test procedures necessary to execute the test case
TEST
Test Items and Features: | Identify and describe the items and features that will be exercised by the test case.Group the test cases into logically related scenarios that test related items and features.For each item or feature,a reference to its associated requirment source should be include.
Input Specifications: | Define each input required to execute the test case and reference any required relationship between inputs.
Procedural Steps: | Describe the sequence of actions necessary to prepare and execute the test case.Provide detailed testprocedures for each test case; explain precisely how each test case will be executed.
Expected Results of Case: | Describe the outcome anticipated from the test case.Specify the criteria to be used to determine whether the item has passed or failed.
ACTUAL RESULTS
Output Specifications: | Define all of the outputs and features required of the test case and provided expected values. While executing the test, record and describe the visually observable outputs as they occure.Produce tangible evedence of the output such as ascreen print. At the conclusion,discreancies between the expected results and the actual results.